PRODUCT REQUIREMENTS DOCUMENT

Research Improvement Plan

Automated Multi-Label ECG Classification using SE-ResNet

| Version v1.0 | Date March 2026 | Status Draft | Target Q1 Journal Submission |
| --- | --- | --- | --- |

01 Overview & Problem Statement Why this work needs to improve

## 1.1  Current State

The existing SE-ResNet ensemble achieves a Macro-AUC of 0.932 and Macro-F1 of 0.642 on PTB-XL Fold 10, with external validation AUROC of 0.844 on Chapman-Shaoxing. While technically competent, the paper in its current form would not clear peer review at a Q1 venue due to missing comparisons, weak statistical rigour, and underdeveloped analysis of failure cases.

## 1.2  Goal

Produce a publication-ready manuscript that meets the methodological standards of journals such as NPJ Digital Medicine, IEEE Transactions on Biomedical Engineering, or Journal of Biomedical Informatics, with a realistic submission target within 3–4 months.

## 1.3  Non-Goals

- Deployment or clinical integration — this PRD covers research and manuscript only.

- Real-time inference optimisation.

- Collection of new proprietary ECG data.

02 Success Metrics Quantitative targets for the improved paper

The following table defines current performance, publication-ready targets, and the priority of each metric.

| Metric | Current | Target | Delta | Priority |
| --- | --- | --- | --- | --- |
| Macro-AUC (PTB-XL Fold 10) | 0.932 | ≥ 0.935 | +0.003 | P2 |
| Macro-F1 (PTB-XL Fold 10) | 0.642 | ≥ 0.670 | +0.028 | P1 |
| F1-HYP (minority class) | 0.418 | ≥ 0.500 | +0.082 | P1 |
| External AUROC (Chapman-Shaoxing) | 0.844 | ≥ 0.870 | +0.026 | P1 |
| ECE (calibration) | < 0.05 | < 0.04 | — | P2 |
| SOTA baselines compared | 0 | ≥ 3 | +3 | P1 |
| Confidence intervals reported | None | All metrics | — | P1 |
| Subgroup analyses (age/sex) | None | 2 variables | — | P2 |
| Ablation table (full component) | Partial | Complete | — | P2 |

P1 = Must-have for submission  |  P2 = Strongly recommended  |  P3 = Nice-to-have

03 Detailed Requirements Organised by priority tier

## 3.1  Priority 1 — Must-Have

### REQ-01: SOTA Baseline Comparisons

Implement or reproduce results from at least three established methods on the identical PTB-XL Fold 10 test split, reported under the same evaluation protocol.

- Ribeiro et al. (2020) — Nature Communications CNN (12-lead, 6-class). Reference implementation available on GitHub.

- PhysioNet/CinC 2020 winner — Top-ranked multi-label model. Use the team's public repository.

- Transformer baseline — At minimum one attention-based model (e.g. ST-MEM, CLOCS, or W2V-BERT-ECG).

Acceptance criteria: all three baselines evaluated on Fold 10 with Macro-AUC, Macro-F1, and per-class F1 reported in a unified comparison table.

### REQ-02: Statistical Validation

All reported metrics must be accompanied by 95% confidence intervals. Model comparisons must include formal significance testing.

- Bootstrap CIs (n=1000 resamples) on AUC, F1, and per-class F1 for the ensemble and all baselines.

- DeLong's test for AUC comparisons between the ensemble and each baseline.

- McNemar's test for pairwise F1 comparisons at optimal thresholds.

Acceptance criteria: every number in the results tables has a CI; p-values reported for all pairwise comparisons against baselines.

### REQ-03: Minority Class Improvement (HYP)

F1-HYP of 0.418 is insufficient for publication. At least two additional strategies must be evaluated and reported.

- Threshold optimisation: sweep decision threshold per class on validation set using F1-maximisation or Youden's J.

- Class-weighted oversampling: SMOTE or random oversampling of HYP samples with appropriate stratification.

- Two-stage training: fine-tune final layers on a class-balanced subset after standard training.

Acceptance criteria: at least one strategy yields F1-HYP >= 0.500. All attempted strategies reported in an ablation table regardless of outcome.

### REQ-04: Expanded External Validation Analysis

The 9-point AUC drop on Chapman-Shaoxing must be investigated and reported as a dedicated subsection, not a single sentence.

- Per-class AUC and F1 on Chapman-Shaoxing, not just aggregate AUROC.

- Analysis of which classes degrade most and a hypothesis for why (demographic mismatch, label scheme differences, recording protocol).

- Test whether simple input re-normalisation (using Chapman statistics) recovers performance.

- Comparison of PTB-XL vs Chapman-Shaoxing dataset characteristics in a summary table (age, sex distribution, class prevalence).

Acceptance criteria: a standalone subsection (min 300 words) with per-class breakdown and at least one domain-adaptation experiment.

## 3.2  Priority 2 — Strongly Recommended

### REQ-05: Full Component Ablation Table

The current augmentation ablation (Figure 4) is partial. A complete table must show the independent contribution of each architectural and training choice.

- Row 1: Plain ResNet (no SE-blocks, BCE loss, no augmentation) — true baseline.

- Row 2: + SE-blocks.

- Row 3: + Focal Loss (no augmentation).

- Row 4: + Mixup augmentation.

- Row 5: + Ensemble (final model).

Acceptance criteria: table with Macro-AUC and Macro-F1 for all five configurations, with CIs.

### REQ-06: Per-Class Calibration Analysis

ECE is currently reported as a single aggregate number. Reviewers in medical AI expect per-class reliability.

- Reliability diagram for each of the five superclasses separately.

- ECE reported per class, not just globally.

- Discussion of which classes are over- vs under-confident and clinical implications.

### REQ-07: Subgroup Analysis

PTB-XL metadata enables analysis of model equity across patient subgroups. At minimum two variables must be reported.

- Age groups: <40, 40–60, 60–80, >80 years — AUC and F1 per group.

- Sex: Male vs female — AUC and F1 per group, with statistical comparison.

Acceptance criteria: subgroup results in a supplementary table with discussion of any significant disparities.

### REQ-08: Uncertainty Quantification

Add a lightweight uncertainty estimate to flag low-confidence predictions, which is a key clinical requirement.

- Monte Carlo Dropout: enable dropout at inference, run 50 forward passes, report mean and std of predicted probabilities.

- Analyse whether high-uncertainty samples correspond to misclassified or ambiguous cases.

- Report the proportion of test samples with uncertainty above a threshold and their accuracy vs the confident subset.

## 3.3  Priority 3 — Nice-to-Have

### REQ-09: Human Cardiologist Benchmark

The gold standard for clinical AI papers is comparison to human expert performance. Even citing existing literature benchmarks is better than no comparison.

- Identify published cardiologist performance on PTB-XL or similar datasets.

- If resources permit: brief annotation study with 2–3 clinical collaborators on a 200-sample subset of Fold 10.

### REQ-10: Transformer Comparison or Integration

Transformer-based models are the current frontier in ECG AI. Including one as either a baseline or a proposed model significantly raises the paper's appeal.

- Minimum: reproduce one Transformer baseline for REQ-01 and include it in comparison tables.

- Stretch goal: hybrid SE-ResNet + Transformer attention head on the final representation layer.

### REQ-11: Related Work Section

The paper currently has no literature review. A proper related work section of 600–800 words covering four eras of ECG AI is required for any journal submission.

- Traditional ML and handcrafted features (pre-2018).

- CNN-based approaches for ECG (2018–2021).

- Attention and Transformer models (2021–present).

- Multi-label vs single-label formulation in ECG literature.

04 Work Breakdown Structure All tasks, effort estimates, and phases

| ID | Task | Effort | Phase | Notes |
| --- | --- | --- | --- | --- |
| W-01 | Implement Ribeiro et al. (2020) baseline on PTB-XL Fold 10 | 1 week | Phase 1 | Use official GitHub repo if available |
| W-02 | Implement PhysioNet/CinC 2020 winning model | 1 week | Phase 1 | Adapt to 5-class PTB-XL superclass scheme |
| W-03 | Implement one Transformer ECG baseline (e.g. ST-MEM) | 1.5 weeks | Phase 1 | Can use pre-trained weights if available |
| W-04 | Bootstrap CI computation for all metrics | 2 days | Phase 1 | n=1000, scipy.stats or sklearn |
| W-05 | DeLong & McNemar significance tests vs all baselines | 2 days | Phase 1 | Use sklearn or pingouin library |
| W-06 | Threshold sweep optimisation per class | 2 days | Phase 1 | Optimise on val set, evaluate on Fold 10 |
| W-07 | SMOTE / oversampling experiment for HYP | 3 days | Phase 1 | Use imbalanced-learn library |
| W-08 | Two-stage fine-tuning experiment for HYP | 3 days | Phase 1 | Freeze backbone, retrain head on balanced set |
| W-09 | Per-class AUC/F1 breakdown on Chapman-Shaoxing | 1 day | Phase 1 | Already have model; extend eval script |
| W-10 | Domain adaptation experiment on Chapman-Shaoxing | 3 days | Phase 1 | Try input re-normalisation and feature alignment |
| W-11 | Full component ablation table (5 configurations) | 1 week | Phase 2 | Retraining needed for plain ResNet rows |
| W-12 | Per-class reliability diagrams and ECE | 2 days | Phase 2 | Extend existing calibration script |
| W-13 | Subgroup analysis by age and sex | 2 days | Phase 2 | PTB-XL metadata already available |
| W-14 | Monte Carlo Dropout uncertainty quantification | 3 days | Phase 2 | Add dropout layers and modify inference loop |
| W-15 | Write Related Work section (600–800 words) | 3 days | Phase 2 | Cover 4 eras of ECG AI literature |
| W-16 | Rewrite Discussion — external validation subsection | 2 days | Phase 2 | Min 300 words, include per-class analysis |
| W-17 | Add Limitations section | 1 day | Phase 2 | Single-centre data, no prospective validation |
| W-18 | Revise Conclusion — remove overclaims | 1 day | Phase 2 | Remove 'viable for clinical workflow' language |
| W-19 | Identify and approach clinical collaborator for cardiologist benchmark | Ongoing | Phase 3 | Optional; significantly raises impact |
| W-20 | Hybrid SE-ResNet + Transformer attention experiment | 2 weeks | Phase 3 | Stretch goal; only if time permits |
| W-21 | Final manuscript revision and journal formatting | 1 week | Phase 3 | Follow target journal author guidelines |

05 Delivery Timeline Three-phase plan to submission

| Phase | Duration | Deliverables | Gate |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1–5 (~5 weeks) | - SOTA baseline comparisons (W-01, W-02, W-03) - Statistical validation — CIs and significance tests (W-04, W-05) - HYP minority class improvement experiments (W-06, W-07, W-08) - Expanded Chapman-Shaoxing analysis (W-09, W-10) | All P1 requirements met. Paper draft updated with new results tables. |
| Phase 2 | Weeks 6–10 (~5 weeks) | - Full ablation table (W-11) - Per-class calibration analysis (W-12) - Subgroup analysis (W-13) - Uncertainty quantification (W-14) - New sections: Related Work, expanded Discussion, Limitations (W-15–W-18) | All P1 and P2 requirements met. Internal review by collaborator or colleague. |
| Phase 3 | Weeks 11–14 (~4 weeks) | - Optional: cardiologist benchmark (W-19) - Optional: Transformer hybrid experiment (W-20) - Final manuscript polish, figures, journal formatting (W-21) - Cover letter and submission | Manuscript submitted to target journal. |

06 Target Publication Venues Ranked by fit and achievability

| Tier | Journal / Venue | IF | Scope Fit | Notes |
| --- | --- | --- | --- | --- |
| A | NPJ Digital Medicine | ~15 | Excellent | Requires clinical validation or collaborator sign-off |
| A | IEEE Trans. Biomed. Engineering | ~4.5 | Excellent | Strong engineering rigour required; ideal fit |
| B | J. Biomedical Informatics | ~4.0 | Very Good | More tolerance for methodological papers without clinical study |
| B | Computers in Biol. & Medicine | ~7.0 | Very Good | Fast review; good for Phase 1+2 complete version |
| C | PLOS ONE | ~3.0 | Good | Broad scope; lower bar; good fallback |
| C | Physiological Measurement | ~3.0 | Good | ECG-specific; very relevant audience |

07 Risks & Mitigations Known obstacles and contingency plans

| Risk | Severity | Mitigation | Contingency |
| --- | --- | --- | --- |
| Baseline model reproduction fails or diverges significantly | High | Use pre-trained weights where available; contact original authors | Report attempted reproduction as a limitation |
| HYP F1 cannot reach 0.500 despite all strategies | Medium | Try ensemble of all HYP-targeted models | Reframe as a rigorous negative result with analysis |
| Compute constraints delay Phase 1 training | Medium | Use PTB-XL 100Hz version (smaller); use cloud spot instances | Reduce baseline count to 2 instead of 3 |
| Chapman-Shaoxing domain gap is irreducible | Low | Analyse gap statistically and report transparently | Reframe external validation as a robustness ceiling analysis |
| Target journal rejects for lack of clinical partner | Medium | Submit to Tier B venue first; build clinical network in parallel | Preprint on arXiv to establish priority while seeking collaborators |

Appendix: Key References for Baseline Implementation

- Ribeiro et al. (2020) — 'Automatic diagnosis of the 12-lead ECG using a deep neural network.' Nature Communications. https://github.com/antonior92/automatic-ecg-diagnosis

- Strodthoff et al. (2021) — 'Deep Learning for ECG Analysis: Benchmarks and Insights from PTB-XL.' IEEE Journal of Biomedical and Health Informatics. Defines the PTB-XL benchmark protocol.

- PhysioNet/CinC Challenge 2020 — 'Classification of 12-lead ECGs: The PhysioNet/Computing in Cardiology Challenge 2020.' https://physionetchallenges.org/2020/

- Mehari & Strodthoff (2022) — 'Self-supervised representation learning from 12-lead ECG data.' Computers in Biology and Medicine. (CLOCS / contrastive baseline)

- Na et al. (2022) — 'ST-MEM: Masked Autoencoders for ECG Pre-training.' arXiv. (Transformer baseline)

GitHub: https://github.com/erfsalehi/Deep-Learning-for-Multi-Class-ECG-Classification